## 4 S-curve
PROGRESS SCHEDULE - CONTRACT 02
| Commencement date |  | : | 2005-02-10 | [13 empty] | Ext. Time for completion | [6 empty] | : |  | 59.5 | [12 empty] | Rev. Scheduled total progress | [6 empty] | : |  | 97.6
| Contract completion date |  | : | 2008-02-09 | [13 empty] | Time elapsed | [6 empty] | : |  | 59.5 | [12 empty] | Actual total progress | [6 empty] | : |  | 88.9
| Extended Completion date |  | : | 2009-12-31 |  |  |  |  | (Expected comp.30 June 2010) | [8 empty] | % Time elapsed | [6 empty] | : |  | 100% | [12 empty] | Ahead (+) / Behind (-) | [6 empty] | : |  | -8.7
[15 empty] | 45 |  |  | 100
[11 empty] | Scheduled duration and percentage accomplishment : | [25 empty] | Scheduled progress :
[11 empty] | Actual duration and percentage accomplished to date : | [25 empty] | Revised Scheduled progress :
[15 empty] | 50 | [21 empty] | Actual progress :
|  |  | 2005 | [10 empty] | 2006 | [11 empty] | 2007 | [11 empty] | 2008 | [11 empty] | 2009 | [11 empty] | 2010
|  |  | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M
| General items |  | 2009 D: 98.39; 2010 J: 98.9267; 2010 F: 99.4633; 2010 M: 100
80.6725
Environmental management plan
100.067
Site clearance
97.4005
Earthworks and drainage
84.5676
Aggregate sub-base and base
99.8121
Bituminous courses
98.5382
Pipe culverts
87.5013
Slab culverts
| Box culverts |  | 2009 D: 100
[23 empty] | 6.4804 | [37 empty] | 66.9574
| Bridges |  | 2009 D: 81.8985; 2010 J: 87.1421; 2010 F: 91.9112; 2010 M: 99.859
66.6906
| Miscellaneous items |  | 2009 D: 99.991; 2010 J: 99.991; 2010 F: 99.991; 2010 M: 99.991
70.987
| Scheduled Progress (%) |  | 0 | 0.0035705 | 0.12469 | 0.55694 | 1.064 | 1.9466 | 2.2895 | 4.3029 | 7.4838 | 7.6949 | 11.9151 | 16.3919 | 22.5311 | 29.138 | 35.1515 | 41.0969 | 46.1268 | 50.9451 | 52.3943 | 57.473 | 62.923 | 67.7013 | 72.3566 | 76.4748 | 80.4061 | 84.2579 | 87.9276 | 91.0543 | 92.0712 | 93.7224 | 39.3763 | 42.493 | 46.5908 | 50.8625 | 56.0357 | 61.4565 | 68.4473 | 75.0315 | 81.9516 | 89.1692 | 58.1928
| Rev Scheduled Progress (%) |  | 2007 A: 39.3763; 2007 S: 42.493; 2007 O: 46.5908; 2007 N: 50.8625; 2007 D: 56.0357; 2008 J: 61.4565; 2008 F: 68.4473; 2008 M: 75.0315; 2008 A: 81.9516; 2008 M: 89.1692; 2008 J: 58.1928; 2008 J: 0; 2008 A: 64.9085; 2008 S: 71.9767; 2008 O: 78.8891
[43 empty] | 58.1928 | 61.8666 | 64.9085 | 71.9767 | 78.8891 | 86.6676 | 94.633 | 101.5577 | 72.7434 | 79.1744 | 86.2628 | 93.5916 | 99.4554 | 100.2434 | 88.3668 | 93.3061 | 95.3846 | 96.3898 | 97.6156 | 98.3075 | 98.9377 | 99.9808
| Actual Progress (%) |  | 2005 F: 0; 2005 M: 0; 2005 A: 0.12969; 2005 M: 0.38394; 2005 J: 0.77951; 2005 J: 1.2962; 2005 A: 1.7594; 2005 S: 1.839; 2005 O: 1.9907; 2005 N: 2.0034; 2005 D: 2.3; 2006 J: 3.0838; 2006 F: 3.5837; 2006 M: 6.8022; 2006 A: 7.9336; 2006 M: 8.7845; 2006 J: 10.3847; 2006 J: 12.1764; 2006 A: 14.9457; 2006 S: 17.4686; 2006 O: 19.453; 2006 N: 20.3718; 2006 D: 22.4775; 2007 J: 25.14; 2007 F: 27.66; 2007 M: 32.2437; 2007 A: 33.781; 2007 M: 36.6419; 2007 J: 39.8484; 2007 J: 42.4219
| Rev Actual Progress (%) |  | 2007 A: 39.3763; 2007 S: 42.1786; 2007 O: 43.7571; 2007 N: 45.2693; 2007 D: 46.7299; 2008 J: 50.6183; 2008 F: 53.3379; 2008 M: 55.6605; 2008 A: 57.8195; 2008 M: 59.8769; 2008 J: 61.2; 2008 J: 62.9; 2008 A: 65.0958
[43 empty] | 61.2 | 62.9 | 65.0958 | 67.4011 | 68.2106 | 69.2019 | 70.1316 | 71.6558 | 72.1433 | 74.2089 | 75.3527 | 77.0545 | 79.005 | 80.7142 | 82.3745 | 84.0548 | 86.0112 | 86.935 | 88.8778
this month ends on |  |  | 2005 F: 2005; 2006 J: 2006; 2007 J: 2007; 2008 J: 2008; 2009 J: 2009; 2010 J: 2010
2009-12-31 | time axis 2005-02-01 to 2010-03-01
| Original Schedule | 0 | 2005-02-01: 3.0131e-05; 2005-03-01: 0.0035705; 2005-04-01: 0.12469; 2005-05-01: 0.55694; 2005-06-01: 1.064; 2005-07-01: 1.9466; 2005-08-01: 2.2895; 2005-09-01: 4.3029; 2005-10-01: 7.4838; 2005-11-01: 7.6949; 2005-12-01: 11.9151; 2006-01-01: 16.3919; 2006-02-01: 22.5311; 2006-03-01: 29.138; 2006-04-01: 35.1515; 2006-05-01: 41.0969; 2006-06-01: 46.1268; 2006-07-01: 50.9451; 2006-08-01: 52.3943; 2006-09-01: 57.473; 2006-10-01: 62.923; 2006-11-01: 67.7013; 2006-12-01: 72.3566; 2007-01-01: 76.4748; 2007-02-01: 80.4061; 2007-03-01: 84.2579; 2007-04-01: 87.9276; 2007-05-01: 91.0543; 2007-06-01: 92.0712; 2007-07-01: 93.7224; 2007-08-01: 95.2346; 2007-09-01: 97.0398; 2007-10-01: 98.4603; 2007-11-01: 99.6214; 2007-12-01: 99.9354; 2008-01-01: 99.9851; 2008-02-01: 100
| Schedule Rev 1 | 0 | 3.0131e-05 | 0.0035705 | 0.12469 | 0.55694 | 1.064 | 1.9466 | 2.2895 | 4.3029 | 7.4838 | 7.6949 | 11.9151 | 16.3919 | 22.5311 | 29.138 | 35.1515 | 41.0969 | 46.1268 | 50.9451 | 52.3943 | 57.473 | 62.923 | 67.7013 | 72.3566 | 76.4748 | 80.4061 | 84.2579 | 87.9276 | 91.0543 | 92.0712 | 93.7224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.9085 | 71.9767 | 78.8891
| Schedule Rev 2 | 0 | 3.0131e-05 | 0.0035705 | 0.12469 | 0.55694 | 1.064 | 1.9466 | 2.2895 | 4.3029 | 7.4838 | 7.6949 | 11.9151 | 16.3919 | 22.5311 | 29.138 | 35.1515 | 41.0969 | 46.1268 | 50.9451 | 52.3943 | 57.473 | 62.923 | 67.7013 | 72.3566 | 76.4748 | 80.4061 | 84.2579 | 87.9276 | 91.0543 | 92.0712 | 93.7224 | 39.3763 | 42.493 | 46.5908 | 50.8625 | 56.0357 | 61.4565 | 68.4473 | 75.0315 | 81.9516 | 89.1692 | 58.1928 | 61.8666 | 64.9085 | 71.9767 | 78.8891 | 86.6676 | 94.633 | 101.5577 | 72.7434 | 79.1744 | 86.2628 | 93.5916 | 99.4554 | 100.2434 | 88.3668 | 93.3061 | 95.3846 | 96.3898 | 97.6156 | 98.3075 | 98.9377 | 99.9808
Schedule Rev 3
|  |  | 0 | 0 | 0.12969 | 0.25425 | 0.39556 | 0.5167 | 0.46317 | 0.079658 | 0.15171 | 0.01264 | 0.29662 | 0.78378 | 0.49992 | 3.2185 | 1.1314 | 0.8509 | 1.6002 | 1.7917 | 2.7693 | 2.5229 | 1.9844 | 0.91876 | 2.1057 | 2.6625 | 2.52 | 4.5837 | 1.5373 | 2.8609 | 3.2065 | 2.5735 |  | 2.8023
| Original achievement | 0 | 2005-02-01: 0; 2005-03-01: 0; 2005-04-01: 0.12969; 2005-05-01: 0.38394; 2005-06-01: 0.77951; 2005-07-01: 1.2962; 2005-08-01: 1.7594; 2005-09-01: 1.839; 2005-10-01: 1.9907; 2005-11-01: 2.0034; 2005-12-01: 2.3; 2006-01-01: 3.0838; 2006-02-01: 3.5837; 2006-03-01: 6.8022; 2006-04-01: 7.9336; 2006-05-01: 8.7845; 2006-06-01: 10.3847; 2006-07-01: 12.1764; 2006-08-01: 14.9457; 2006-09-01: 17.4686; 2006-10-01: 19.453; 2006-11-01: 20.3718; 2006-12-01: 22.4775; 2007-01-01: 25.14; 2007-02-01: 27.66; 2007-03-01: 32.2437; 2007-04-01: 33.781; 2007-05-01: 36.6419; 2007-06-01: 39.8484; 2007-07-01: 42.4219; 2007-10-01: 42.4219; 2007-11-01: 42.4219; 2007-12-01: 42.4219; 2008-01-01: 42.4219; 2008-02-01: 42.4219
| Achievement Rev 1 | 0 | 0 | 0 | 0.12969 | 0.5 | 0.77951 | 1.2962 | 1.7594 | 1.839 | 1.9907 | 2.0034 | 2.3 | 3.0838 | 3.5837 | 6.8022 | 7.9336 | 8.7845 | 10.3847 | 12.1764 | 14.9457 | 17.4686 | 19.453 | 20.3718 | 22.4775 | 25.14 | 27.66 | 32.2437 | 33.781 | 36.6419 | 39.8484 | 42.4219 | 39.3763 | 42.1786 | 43.7571 | 45.2693 | 46.7299 | 50.6183 | 53.3379 | 55.6605 | 57.8195 | 59.8769 | 61.2 | 62.9 | 65.0958 | 67.4011 | 68.2106 | 69.2019 | 70.1316 | 71.6558 | 72.1433 | 74.2089 | 75.3527 | 77.0545 | 79.005 | 80.7142 | 82.3745 | 84.0548 | 86.0112 | 86.935 | 88.8778
| Achievement Rev 2 | 0 | 0 | 0 | 0.12969 | 0.38394 | 0.77951 | 1.2962 | 1.7594 | 1.839 | 1.9907 | 2.0034 | 2.3 | 3.0838 | 3.5837 | 6.8022 | 7.9336 | 8.7845 | 10.3847 | 12.1764 | 14.9457 | 17.4686 | 19.453 | 20.3718 | 22.4775 | 25.14 | 27.66 | 32.2437 | 33.781 | 36.6419 | 39.8484 | 42.4219 | 39.3763 | 42.1786 | 43.7571 | 45.2693 | 46.7299 | 50.6183 | 53.3379 | 55.6605 | 57.8195 | 59.8769
Achievement Rev 3

## Phy.Pro.30.12.09
TAMIL NADU ROAD SECTOR PROJECT
IBRD Loan Acount No. 4706 - IN
Physical Progress
For the Quarter ending December 2009
Component Code : CA 02
Descripition of Contract : Nagapattinam to Kattumavadi
Name of Contractor : M/s. IRCON International & SMJ Indonesia JV
Activity | Unit | Total | Revised | Total up to last quarter |  |  | Total this quarter |  |  | Total to date
|  |  |  | Target | Actual | Variance | Target | Actual | Variance | Target | Actual | Variance
(x1000)
General items | INR | 66960 | 43058.414 | 82.2939 | 78.0002 | 4.2937 | 16.0961 | 2.6723 | -13.4238 | 98.39 | 80.6725 | -17.7176
Environmental management | INR | 10615 | 10391.187 | 100 | 97.1058 | 2.8942 | 0 | 2.9611 | 2.9611 | 100 | 100.067 | 0.066994
Site clearance | INR | 8516 | 25438.124 | 99.9996 | 96.6177 | 3.3819 | 0 | 0.7828 | 0.7828 | 99.9996 | 97.4005 | -2.5991
Earthworks and drainage structures | INR | 415390 | 466831.054 | 99.9994 | 82.4741 | 17.5253 | 0 | 2.0934 | 2.0934 | 99.9994 | 84.5676 | -15.4319
Sub-base and base | INR | 479855 | 670286.528 | 100 | 96.4842 | 3.5158 | 0 | 3.328 | 3.328 | 100 | 99.8121 | -0.18789
Bituminous pavement | INR | 486703 | 378720.04 | 100 | 91.6218 | 8.3782 | 0 | 6.9164 | 6.9164 | 100 | 98.5382 | -1.4618
Pipe culverts | INR | 41362 | 48696.352 | 99.9953 | 75.9317 | 24.0637 | 0 | 11.5696 | 11.5696 | 99.9953 | 87.5013 | -12.4941
Slab culverts | INR | 103807 | 78900.508 | 100 | 92.9891 | 7.0109 | 0 | 4.4376 | 4.4376 | 100 | 97.4266 | -2.5734
Box culverts | INR | 24431 | 28649.522 | 85.5201 | 53.1916 | 32.3285 | 14.4799 | 13.7658 | -0.71404 | 100 | 66.9574 | -33.0426
Bridges | INR | 232021 | 283525.3276 | 64.0458 | 54.3912 | 9.6547 | 17.8526 | 12.2994 | -5.5532 | 81.8985 | 66.6906 | -15.2079
Miscellaneous items | INR | 112197 | 147793.986 | 78.1014 | 72.7663 | 5.3351 | 21.8897 | -1.7793 | -23.669 | 99.991 | 70.987 | -29.0041

## Fin.Pro.31.12.09
TAMIL NADU ROAD SECTOR PROJECT
IBRD Loan Acount No. 4706 - IN
Financial Progress Details
For the Quarter ending December 2009
Component Code :CA 02
Descripition of Contract :Upgrading of Roads from Nagapattinam to Kattumavadi
Name of Contractor :M/s. IRCON International & SMJ Indonesia JV
Activity | Unit | Physical % progress to date |  | Cost to date (Rupees) |  |  | Cost to completion (Rupees)
|  | Target | Actual | Target | Actual | Actual as % of target | Original |  | Revised
|  |  |  | (x1000) |  |  | (x1,000) | Date | (x1,000) | Date
General items | INR | 98.39 | 80.6725 | 42365.189 | 34736.2871 | 81.9925 | 66960 | 2008-02-09 | 43058.414 | 2008-10-31
Environmental management | INR | 100 | 100.067 | 10391.187 | 10398.1485 | 100.067 | 10615 | 2008-02-09 | 10391.187 | 2008-10-31
Site clearance | INR | 99.9996 | 97.4005 | 25438.024 | 24776.8597 | 97.4009 | 8516 | 2008-02-09 | 25438.124 | 2008-10-31
Earthworks and drainage structures | INR | 99.9994 | 84.5676 | 466828.337 | 394787.6684 | 84.5681 | 415390 | 2008-02-09 | 466831.054 | 2008-10-31
Sub-base and base | INR | 100 | 99.8121 | 670286.528 | 669027.1475 | 99.8121 | 479855 | 2008-02-09 | 670286.528 | 2008-10-31
Bituminous pavement | INR | 100 | 98.5382 | 378720.04 | 373183.8053 | 98.5382 | 486703 | 2008-02-09 | 378720.04 | 2008-10-31
Pipe culverts | INR | 99.9953 | 87.5013 | 48694.087 | 42609.9285 | 87.5053 | 41362 | 2008-02-09 | 48696.352 | 2008-10-31
Slab culverts | INR | 100 | 100 | 78900.508 | 78900.508 | 100 | 103807 | 2008-02-09 | 78900.508 | 2008-10-31
Box culverts | INR | 100 | 66.9574 | 28649.522 | 19182.9858 | 66.9574 | 24431 | 2008-02-09 | 28649.522 | 2008-10-31
Bridges | INR | 81.8985 | 66.6906 | 232202.8572 | 189084.6669 | 81.4308 | 232021 | 2008-02-09 | 283525.3276 | 2008-10-31
Miscellaneous items | INR | 99.991 | 70.987 | 147780.753 | 104914.4827 | 70.9933 | 112197 | 2008-02-09 | 147793.986 | 2008-10-31
Total | INR |  |  | 2130257.0322 | 1941602.4885 |  | 1981857 |  | 2182291.0426

## Qua.Fin.Req.31.12.09
TAMIL NADU ROAD SECTOR PROJECT
IBRD Loan Acount No. 4706 - IN
Estimated Quarterly Financial Requirement
For the Quarter ending December 2009
Component Code :CA 02
Descripition of Contract :Upgrading of Roads from Nagapattinam to Kattumavadi
Name of Contractor :M/s. IRCON International & SMJ Indonesia JV
Activity | Unit | 2008 | 2009 |  |  |  | 2010
|  | 4 | 1 | 2 | 3 | 4 | 1
x1000
General items | INR | 31426 | 96 | 0 | 0
Env. Management | INR | 4567 | 325 | 0 | 0
Site clearance | INR | 5177 | 0 | 0 | 0
Earthworks and drainage structures | INR | 117786 | 36963 | 0 | 0
Sub-base and base | INR | 109138 | 25754 | 0 | 0
Bituminous pavement | INR | 66590 | 34360 | 0 | 0
Pipe culverts | INR | 9538 | 3348 | 0 | 0
Slab culverts | INR | 2845 | 838 | 0 | 0
Box culverts | INR | 20165 | 190 | 0 | 0
Bridges | INR | 70704 | 77416 | 25443 | 6818
Miscellaneous items | INR | 58915 | 18195 | 0 | 0
Total | INR | 496851 | 197485 | 25443 | 6818 | 726597