## 4 S-curve
PROGRESS SCHEDULE - CONTRACT 04
| Commencement date |  | : | 2005-12-16 | [10 empty] | Time for completion |  |  |  |  | : | 49.2 | [14 empty] | Planned total progress | [6 empty] | : | 100
| Contract completion date |  | : | 2008-12-15 | [10 empty] | Time elapsed |  |  |  |  | : | 49.2 | [14 empty] | Actual total progress | [6 empty] | : | 91.0013
| Extended Completion date |  | : | 2009-12-31 | [10 empty] | % Time elapsed |  |  |  |  | : | 100% | [14 empty] | Ahead (+) / Behind (-) | [6 empty] | : | -9
[15 empty] | 45 |  |  | 100
[11 empty] | Scheduled duration and percentage accomplishment : | [16 empty] | Scheduled progress :
[11 empty] | Actual duration and percentage accomplished to date : | [16 empty] | Revised Scheduled progress :
[15 empty] | 50 | [12 empty] | Actual progress :
|  |  | 2005 | 2006 | [11 empty] | 2007 | [11 empty] | 2008 | [11 empty] | 2009
|  |  | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| General items |  | 2009 D: 100
92.938
| Environmental management plan |  | 2006 J: 0.73298; 2006 J: 0.73298; 2006 S: 2.6097; 2006 O: 2.6097; 2009 D: 100
49.7068
| Site clearance |  | 2006 S: 19.1249; 2006 O: 19.1249; 2006 N: 19.1249; 2009 D: 100
51.0372
| Earthworks and drainage |  | 2009 D: 100
91.3212
| Aggregate sub-base and base |  | 2009 D: 100
95.5424
| Bituminous courses |  | 2009 D: 100
96.8299
| Pipe culverts |  | 2009 D: 100
91.611
| Slab culverts |  | 2009 D: 100
100
| Box culverts |  | 2006 J: 23.8152; 2006 A: 23.8152; 2006 S: 23.8152; 2006 O: 23.8152; 2006 N: 23.8152; 2006 D: 23.8152; 2009 D: 100
92.3245
| Bridges |  | 2009 D: 100
63.6832
| Miscellaneous items |  | 2006 J: 17.1987; 2006 A: 17.1987; 2006 S: 17.1987; 2006 O: 17.1987; 2006 N: 17.1987; 2006 D: 17.1987; 2009 D: 100
48.7332
| Scheduled Progress (%) |  | 0 | 0 | 0.0083155 | 0.36595 | 1.4498 | 3.1033 | 5.1342 | 7.3351 | 10.4305 | 12.5077 | 14.4322 | 16.4278 | 20.5341 | 24.7787 | 29.164 | 33.8163 | 38.5974 | 43.3888 | 48.4191 | 53.0545 | 57.5733 | 59.703 | 61.5952 | 63.7122 | 68.2407 | 72.6448 | 76.6779 | 80.0296 | 83.03 | 86.3401 | 89.4467 | 92.5194 | 95.4418 | 97.3993 | 99.2384 | 99.9811 | 100
| Rev.Scheduled Progress (%) |  | 2007 A: 7.8558; 2007 S: 9.9496; 2007 O: 13.0179; 2007 N: 17.3465; 2007 D: 22.01; 2008 J: 27.0189; 2008 F: 33.3919; 2008 M: 41.8671; 2008 A: 50.2297; 2008 M: 58.633; 2008 J: 67.3739; 2008 J: 75.0258; 2008 A: 83.5609; 2008 S: 91.6; 2008 O: 45.9876; 2008 N: 50.3752; 2008 D: 55.3396; 2009 J: 60.9373; 2009 F: 66.6255; 2009 M: 72.0662; 2009 A: 77.4743
[37 empty] | 45.9876 | 50.3752 | 55.3396 | 60.9373 | 66.6255 | 72.0662 | 77.4743 | 81.5506 | 82.7248 | 86.8696 | 91.1098 | 96.371 | 88.9329 | 95.0404 | 100
| Actual Progress (%) |  | 2005 D: 0; 2006 J: 0; 2006 F: 0; 2006 M: 0; 2006 A: 0; 2006 M: 0; 2006 J: 0; 2006 J: 0; 2006 A: 3.6468; 2006 S: 3.925; 2006 O: 3.9934; 2006 N: 4.3869; 2006 D: 4.407; 2007 J: 5.0444; 2007 F: 5.9574; 2007 M: 8.0275; 2007 A: 10.7523; 2007 M: 11.2204; 2007 J: 11.8585; 2007 J: 14.3423; 2007 A: 16.5947
| Rev.Actual Progress (%) |  | 2007 S: 9.4079; 2007 O: 11.0661; 2007 N: 12.2159; 2007 D: 14.0431; 2008 J: 17.7771; 2008 F: 20.2525; 2008 M: 22.7097; 2008 A: 25.7119; 2008 M: 28.9183; 2008 J: 32.044; 2008 J: 36.3637; 2008 A: 40.8705; 2008 S: 45.8694
[37 empty] | 46.2249 | 48.2276 | 51.5009 | 55.781 | 60.2527 | 64.6244 | 67.9118 | 73.2188 | 75.9889 | 80.0264 | 84.595 | 86.5577 | 87.879 | 88.7285 | 91.0013
this month ends on |  |  | 2005 D: 2005; 2006 J: 2006; 2007 J: 2007; 2008 J: 2008; 2009 J: 2009
2009-12-31 | time axis 2006-01-01 to 2009-12-01
| Original Schedule | 0 | 0 | 0 | 0.0083155 | 0.36595 | 1.4498 | 3.1033 | 5.1342 | 7.3351 | 10.4305 | 12.5077 | 14.4322 | 16.4278 | 20.5341 | 24.7787 | 29.164 | 33.8163 | 38.5974 | 43.3888 | 48.4191 | 53.0545 | 57.5733 | 59.703 | 61.5952 | 63.7122 | 68.2407 | 72.6448 | 76.6779 | 80.0296 | 83.03 | 86.3401 | 89.4467 | 92.5194 | 95.4418 | 97.3993 | 99.2384 | 99.9811 | 100
| Schedule Rev 1 | 0 | 0 | 0 | 0.0083155 | 0.36595 | 1.4498 | 3.1033 | 5.1342 | 7.3351 | 10.4305 | 12.5077 | 14.4322 | 16.4278 | 20.5341 | 24.7787 | 29.164 | 33.8163 | 38.5974 | 43.3888 | 48.4191 | 53.0545 | 7.8558 | 9.9496 | 13.0179 | 17.3465 | 22.01 | 27.0189 | 33.3919 | 41.8671 | 50.2297 | 58.633 | 67.3739 | 75.0258 | 83.5609 | 91.6054 | 45.9876 | 50.3752 | 55.3396 | 60.9373 | 66.6255 | 72.0662 | 77.4743 | 81.5506 | 82.7248 | 86.8696 | 91.1098 | 96.371 | 88.9329 | 95.0404 | 100
| Schedule Rev 2 |  | 2008-10-01: 45.9876; 2008-11-01: 50.3752; 2008-12-01: 55.3396; 2009-01-01: 60.9373; 2009-02-01: 66.6255; 2009-03-01: 72.0662; 2009-04-01: 77.4743; 2009-05-01: 81.5506; 2009-06-01: 82.7248; 2009-07-01: 86.8696; 2009-08-01: 91.1098; 2009-09-01: 96.371; 2009-10-01: 88.9329; 2009-11-01: 95.0404; 2009-12-01: 100
Schedule Rev 3
| Original achievement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6468 | 3.925 | 3.9934 | 4.3869 | 4.407 | 5.0444 | 5.9574 | 8.0275 | 10.7523 | 11.2204 | 11.8585 | 14.3423 | 16.5947 | 1.6877 |  | 16.5947 | 16.5947 | 16.5947 | 16.5947 | 16.5947 | 16.5947 | 16.5947 | 16.5947 | 16.5947 | 16.5947 | 16.5947 | 16.5947 | 16.5947 | 16.5947
| Achievement Rev 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6468 | 3.925 | 3.9934 | 4.3869 | 4.407 | 5.0444 | 5.9574 | 8.0275 | 10.7523 | 11.2204 | 11.8585 | 14.3423 | 7.7201 | 9.4079 | 11.0661 | 12.2159 | 14.0431 | 17.7771 | 20.2525 | 22.7097 | 25.7119 | 28.9183 | 32.044 | 36.3637 | 40.8705 | 45.8694 | 46.2249 | 48.2276 | 51.5009 | 55.781 | 60.2527 | 64.6244 | 67.9118 | 73.2188 | 75.9889 | 80.0264 | 84.595 | 86.5577 | 87.879 | 88.7285 | 91.0013
Achievement Rev 2
Achievement Rev 3

## Phy.Pro.31.12.09
TAMIL NADU ROAD SECTOR PROJECT
IBRD Loan Acount No. 4706 - IN
Physical Progress Report
For the Quarter ending December 2009
Component Code : CA 04
Descripition of Contract : Ramanathapuram to Tuticorin
Name of Contractor : M/s. R.N. Shetty & Co. Pvt. Ltd - Gayatri Projects Ltd (JV)
Activity | Unit | Total | Revised | Total up to last quarter |  |  | Total during this quarter |  |  | Total to date
|  |  |  | Target | Actual | Variance | Target | Actual | Variance | Target | Actual | Variance
(x1000)
General items | INR | 18245 | 19402.38 | 89.961 | 87.388 | -2.573 | 10.039 | 5.55 | -4.489 | 100 | 92.938 | -7.062
Environmental management | INR | 7449 | 7449 | 73.1534 | 66.0136 | -7.1398 | 26.8466 | -16.3068 | -43.1534 | 100 | 49.7068 | -50.2932
Site clearance | INR | 6397 | 13524.9 | 50.999 | 51.0085 | 0.0094909 | 49.001 | 0.028706 | -48.9723 | 100 | 51.0372 | -48.9628
Earthworks and drainage structures | INR | 141321 | 454049.2794 | 92.0698 | 90.2141 | -1.8557 | 7.9302 | 1.1072 | -6.8231 | 100 | 91.3212 | -8.6788
Sub-base and base | INR | 328992 | 434144.373 | 93.3569 | 93.3568 | -0.00012381 | 6.6431 | 2.1856 | -4.4574 | 100 | 95.5424 | -4.4576
Bituminous pavement | INR | 486344 | 421550.961 | 92.705 | 94.5074 | 1.8024 | 7.295 | 2.3225 | -4.9725 | 100 | 96.8299 | -3.1701
Pipe culverts | INR | 24925 | 40694.061 | 79.0422 | 77.9761 | -1.0661 | 20.9578 | 2.0406 | -18.9172 | 100 | 80.0168 | -19.9832
Slab culverts | INR | 71607 | 29673.642 | 71.9258 | 71.9807 | 0.054854 | 28.0742 | 16.7793 | -11.2949 | 100 | 88.76 | -11.24
Box culverts | INR | 9448 | 17363.1 | 76.3738 | 76.4355 | 0.061717 | 23.6262 | 15.889 | -7.7372 | 100 | 92.3245 | -7.6755
Bridges | INR | 56639 | 56639.2946 | 70.4354 | 56.0476 | -14.3878 | 29.5646 | 7.6356 | -21.929 | 100 | 63.6832 | -36.3168
Miscellaneous items | INR | 36085 | 53571.609 | 42.5724 | 41.4447 | -1.1277 | 57.4276 | 7.2886 | -50.139 | 100 | 48.7332 | -51.2668

## Fin.Pro.31.12.09
TAMIL NADU ROAD SECTOR PROJECT
IBRD Loan Acount No. 4706 - IN
Financial Progress Report
For the Quarter ending December 2009
Component Code : CA 04
Descripition of Contract : Ramanathapuram to Tuticorin
Name of Contractor : M/s. R.N. Shetty & Co. Pvt. Ltd - Gayatri Projects Ltd (JV)
Activity | Unit | Physical % progress to date |  | Cost to date (Rupees) |  |  | Cost to completion (Rupees)
|  |  |  | Target | Actual | Actual as % of target | Original |  | Revised
|  | Target | Actual | (x1000) |  |  | (x1,000) | Date | (x1,000) | Date
General items | INR | 100 | 92.938 | 19402.38 | 18032.1882 | 92.938 | 18245 | 2008-02-09 | 22737 | 2009-12-31
Environmental management | INR | 100 | 49.7068 | 7449 | 3702.6564 | 49.7068 | 7449 | 2008-02-09 | 7449 | 2009-12-31
Site clearance | INR | 100 | 51.0372 | 13524.9 | 6902.7255 | 51.0372 | 6397 | 2008-02-09 | 13679 | 2009-12-31
Earthworks and drainage structures | INR | 100 | 91.3212 | 454049.2794 | 414643.3836 | 91.3212 | 141321 | 2008-02-09 | 445049 | 2009-12-31
Sub-base and base | INR | 100 | 95.5424 | 434144.373 | 414792.1427 | 95.5424 | 328992 | 2008-02-09 | 434144.373 | 2009-12-31
Bituminous pavement | INR | 100 | 96.8299 | 421550.961 | 408187.3786 | 96.8299 | 486344 | 2008-02-09 | 423485 | 2009-12-31
Pipe culverts | INR | 100 | 91.611 | 40694.061 | 37280.2563 | 91.611 | 24925 | 2008-02-09 | 40693 | 2009-12-31
Slab culverts | INR | 100 | 88.76 | 29673.642 | 26338.311 | 88.76 | 71607 | 2008-02-09 | 31538 | 2009-12-31
Box culverts | INR | 100 | 92.3245 | 17363.1 | 16030.3997 | 92.3245 | 9448 | 2008-02-09 | 17487 | 2009-12-31
Bridges | INR | 100 | 63.6832 | 56639.2946 | 36069.7092 | 63.6832 | 56639 | 2008-02-09 | 64489 | 2009-12-31
Miscellaneous items | INR | 100 | 48.7332 | 53571.609 | 26107.184 | 48.7332 | 36085 | 2008-02-09 | 54045 | 2009-12-31
Total | INR |  |  | 1548062.6 | 1408086.3352 |  | 1187452 |  | 1554795.373

## Qua.Fin.Req.31.12.09
TAMIL NADU ROAD SECTOR PROJECT
IBRD Loan Acount No. 4706 - IN
Quarterly Financial Requirement
For the Quarter ending December 2009
Component Code : CA 04
Descripition of Contract : Ramanathapuram to Tuticorin
Name of Contractor : M/s. R.N. Shetty & Co. Pvt. Ltd - Gayatri Projects Ltd (JV)
Activity | Unit | 2008 | 2009
|  | 1 | 1 | 2 | 3 | 4
(x1000)
General items | INR | 1544.7866 | 737 | 1006 | 2261 | 20
Env. Management | INR | 1547.9022 | 2324 | 1976 | 826 | 239
Site clearance | INR | 2629.26 | 3842 | 2548 | 1019 | 0
Earthworks and drainage structures | INR | 61795.2378 | 78417 | 81256 | 35083 | 4320
Sub-base and base | INR | 59911.9235 | 51789 | 44219 | 63035 | 8341
Bituminous pavement | INR | 35958.297 | 56238 | 42862 | 42629 | 28104
Pipe culverts | INR | 7154.0159 | 8264 | 7325 | 4573 | 0
Slab culverts | INR | 4465.8831 | 4925 | 4559 | 5106 | 0
Box culverts | INR | 4464.053 | 4867 | 3521 | 1403 | 0
Bridges | INR | 13211.115 | 24161 | 17607 | 1885 | 628
Miscellaneous items | INR | 388.2716 | 14336 | 8318 | 11102 | 6074
Total | INR | 193070.7457 | 249900 | 215197 | 168922 | 47726