## Phy.Pro.31.12.09
TAMIL NADU ROAD SECTOR PROJECT
IBRD Loan Acount No. 4706 - IN
Physical Progress
For the Quarter ending December 2009
Construction Supervision Consultancy Services (SC 02) for Contract Packages TNRSP-02,03 & 04
Component Code : CA 12
Name of Contractor : M/s. Sheladia Associate Inc.U.S.A.,
Activity | Unit | Total (x1000) | EOT-1 | EOT-2 |  | Total to last quarter |  |  | Total this quarter |  |  | Total to date
[5 empty] | Revised | Planned | Actual | Variance | Planned | Actual | Variance | Planned | Actual | Variance
(x1000)
Remuneration - LC
Local key and sub-key staff | INR | 45972.204 | 12333.219 | 12079.852 | 70385.275 | 3216.214 | 2871868 | -15711.8023 | 135 | -2871868 | -2872003 | 3351.214 | 0 | -3351.214
Supporting staff | INR | 4404.988 | 1198.253 | 1761.372 | 7364.613 | 2379.076 | 1137236 | -56.3886 | 465.69 | -1137236 | -1137701.69 | 2844.766 | 0 | -2844.766
Reimbursables - LC
Transportation | INR | 1500 | -827.444 | 65.445 | 738.001 | 1590.259 | 1504887.164 | -1384.012 | 65.826 | -1504887.164 | -1504952.99 | 1656.085 | 0 | -1656.085
Duty travel to site | INR | 550.008 | 240 | -144.6 | 645.408 | 0 | 0 | -304.608 | 0 | 0 | 0 | 0 | 0 | 0
Office rent | INR | 0 | 0 |  | 0 | 66.146 | 51654.58 | 0 | 5.35 | -51654.58 | -51659.93 | 71.496 | 0 | -71.496
Office supplies, utilities etc. | INR | 3157.992 | -747.133 | 659.078 | 3069.937 | 168.8186 | 161968.0767 | -1950.406 | 8.8 | -161968.0767 | -161976.8767 | 177.6186 | 0 | -177.6186
Office furniture and equipment | INR | 171.4 | 0 | 0 | 171.4 | 0 | 0 | -150.122 | 0 | 0 | 0 | 0 | 0 | 0
Printing reports and documents | INR | 293 | 147.95 | 73.2 | 514.15 | 0 | 0 | -416.05 | 0 | 0 | 0 | 0 | 0 | 0
Surveys | INR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Accommodation for expat staff | INR | 3024 | 4.814 | 367.4 | 3396.214 | 70385.275 | 0 | -1250.325 | 0 | 0 | 0 | 70385.275 | 0 | -70385.275
Purchase of software | INR | 3000 | 0 | 0 | 3000 | 51554.6676 | 0 | -3872.764 | 0 | 0 | 0 | 51554.6676 | 0 | -51554.6676
Remuneration - FC
For expatriate staff | USD | 1353.15 | 160.062 | 164.809 | 1678.021 | 0 | 0 | -391.3474 | 0 | 0 | 0 | 0 | 0 | 0
Reimbursables - FC
Mobilisation and demobilisation | USD | 75.65 | -7.039 | 3.035 | 71.646 | 0 | 0 | -65.7994 | 0 | 0 | 0 | 0 | 0 | 0
Other costs | USD | 130.6 | 25.351 | 23.022 | 178.973 | 0 | 0 | -6.9818 | 0 | 0 | 0 | 0 | 0 | 0

## Fin.Pro.31.12.09
TAMIL NADU ROAD SECTOR PROJECT
IBRD Loan Acount No. 4706 - IN
Financial Progress Details
For the Quarter ending December 2009
Construction Supervision Consultancy Services (SC 02) for Contract Packages TNRSP-02,03 & 04
Component Code : CA 12
Name of Contractor : M/s. Sheladia Associate Inc.U.S.A.,
Activity | Unit | Physical % progress to date |  | Cost to date (Rupees) |  |  | Cost to completion (Rupees)
|  |  |  | Planned | Actual* | Actual | Original |  | Revised
|  | Planned | Actual* | (x1000) |  | (%) | (x1,000) | Date | (x1,000) | Date
Remuneration - LC
Local key and sub-key staff * | INR | 100 | 102.8946 | 70385.2746 | 72422.6647 | 102.8946 | 45972.204 | 2008-02-09 | 24413.071 | 2009-12-31
Supporting staff * | INR | 99.9997 | 105.4259 | 7364.589 | 7911.5044 | 107.4263 | 4404.988 | 2008-02-09 | 2959.625 | 2009-12-31
Reimbursables - LC
Transportation | INR | 99.9999 | 77.0802 | 738 | 568.853 | 77.0804 | 1500 | 2008-02-09 | -761.999 | 2009-12-31
Duty travel to site | INR | 99.9994 | 93.4138 | 645.404 | 602.9 | 93.4144 | 550.008 | 2008-02-09 | 95.4 | 2009-12-31
Office rent | INR |  |  |  |  | 0 | 0 | 2008-02-09 | 0 | 2009-12-31
Office supplies, utilities etc. | INR | 99.9999 | 92.8674 | 3069.935 | 2850.971 | 92.8675 | 3157.992 | 2008-02-09 | -88.055 | 2009-12-31
Office furniture and equipment | INR | 99.9988 | 58.3944 | 171.398 | 100.088 | 58.3951 | 171.4 | 2008-02-09 | 0 | 2009-12-31
Printing reports and documents | INR | 99.9984 | 42.1959 | 514.142 | 216.95 | 42.1965 | 293 | 2008-02-09 | 221.15 | 2009-12-31
Surveys | INR |  |  |  |  | 0 | 0 | 2008-02-09 | 0 | 2009-12-31
Accommodation for expat staff | INR | 100 | 87.4925 | 3396.214 | 2971.431 | 87.4925 | 3024 | 2008-02-09 | 372.214 | 2009-12-31
Purchase of software | INR | 99.9999 | 37.9079 | 2999.996 | 1137.236 | 37.9079 | 3000 | 2008-02-09 | 0 | 2009-12-31
Total | INR |  |  | 89284.9526 | 88782.5981 |  | 62073.592 |  | 27211.406
Remuneration - FC
For expatriate staff * | USD | 100.0004 | 92.9655 | 1678.027 | 1559.9802 | 92.9651 | 1353.15 | 2008-02-09 | 324.871 | 2009-12-31
Reimbursables - FC
Mobilisation and demobilisation | USD | 100 | 77.718 | 71.646 | 55.6818 | 77.718 | 75.65 | 2008-02-09 | -4.004 | 2009-12-31
Other costs | USD | 99.9976 | 93.028 | 178.9686 | 166.4951 | 93.0303 | 130.6 | 2008-02-09 | 48.373 | 2009-12-31
Total | USD |  |  | 1928.6416 | 1782.1571 |  | 1559.4 |  | 369.24

## Qua.Fin.Req.31.12.09
TAMIL NADU ROAD SECTOR PROJECT
IBRD Loan Acount No. 4706 - IN
Estimated Quarterly Financial Requirement
For the Quarter ending December 2009
Construction Supervision Consultancy Services (SC 02) for Contract Packages TNRSP-02,03 & 04
Component Code : CA 12
Name of Contractor:M/s. Sheladia Associate Inc.U.S.A.,
Activity | Unit | 2009
|  | 1 | 2 | 3 | 4
(x1000)
Remuneration - LC
Local key and sub-key staff | INR | 5238 | 4238 | 4238 | 3000
Supporting staff | INR | 445 | 445 | 445 | 445
Reimbursables - LC
Transportation | INR | 83 | 83 | 83 | 83
Duty travel to site | INR | 73 | 73 | 73 | 73
Office rent | INR | 0 | 0 | 0 | 0
Office supplies, utilities etc. | INR | 247 | 247 | 247 | 247
Office furniture and equipment | INR | 19 | 19 | 19 | 19
Printing reports and documents | INR | 70 | 70 | 70 | 70
Surveys | INR | 0 | 0 | 0 | 0
Accommodation for expat staff | INR | 204 | 204 | 204 | 204
Purchase of software | INR | 466 | 466 | 466 | 466
Total | INR | 6845 | 5845 | 5845 | 4607
Remuneration - FC
For expatriate staff | USD | 110 | 104 | 104 | 104
Reimbursables - FC
Mobilisation and demobilisation | USD | 6 |  | 7 | 7
Other costs | USD | 8.79 | 4.8 | 4.8 | 4.8
Total | USD | 124.79 | 108.8 | 115.8 | 115.8