PUBLIC-PRIVATE-PARTNERSHIP

| Name of the work | : | Transaction Advisory Services for Feasibility Study and Possible Public Private Partnership (PPP) procurement of State Roads. |
| --- | --- | --- |
| Name of the Consultant | : | M/s. Pricewaterhouse Cooper (P) Ltd., JV with M/s. Lea Associates. |
| Date of commencement of services | : | 27.09.2007 |
| Date of signing of Agreement | : | 12.09.2007 |
| Contractor Price | : | 31,554.375 (excluding service Tax) |
| Total period of contract | : | 15 months |
| Completion period | : | 26.12.2008 |
| Extension of Time (EOT) | : | 31.10.09 |
| Extension of Time (EOT) Requested upto | : | 15.12.09 (NOC to be obtained from World Bank) |

The following four roads were short listed:

- Coimbatore Western Bypass 30km

- Hogenekkal-Pennagaram-Dharmapuri Road (SH-60) 46km

- Vridhachalam-Tholudur Road 45km

- Vridhachalam-Ulundurpet-Villupuram Road 22km

| Task I | (i) Submission and approval of Inception Report | Submitted and Approved. Payment made |
| --- | --- | --- |
|  | (ii) Submission and approval of Draft Techno Economic Feasibility Report (except LPS) for all four roads. | Report submitted and approved. |
|  | (iii) Submission and approval Final Techno Economic Feasibility Report for three roads excluding Coimbatore western bypass. (except LPS) | Report submitted and approved for three roads. The final report for Coimbatore western bypass is to be submitted to the Review Committee for approval. |
|  | Submission and approval of detailed Land Plan Schedule |  |
| Task II | (i) Submission and approval of PPP agreement Project Road Toll Rates | On approval of Task I further work will commence. |
|  | (ii) Submission of PPP agreement and Report to the Central Govt for VGF fundinmg |  |
|  | (iii) Success Fee payable only if and when in principle approval of GOI obtained |  |
| Task III | (i) Submission and approval of PPP Bid Documents | On approval of Task II further work will commence. |
|  | (ii) Submission and approval of Evaluation of bids and evaluation report |  |
|  | (iii) Finalisation and approval of PPP Project Agreement, Discussions, Management Approvals |  |