## LA-31.12.09
Tamil Nadu Road Sector Project
Pre construction activities as on 31.12.2009
Status on Land Registration through Private Negotiation:
Package | Actual Target (Hect.) | Private Negotiation Completed as on 31.12.2009 (Hect) | Registration Completed as on 31.12.2009
TNRSP 01 | 263.0335 | 262.8617 | 262.8617
TNRSP 02 | 87.4583 | 87.4583 | 87.4583
TNRSP 03 | 14.1348 | 14.1348 | 14.1348
TNRSP 04 | 31.0324 | 30.8924 | 30.8924
TNRSP 05 Ramanathapuram Bypass | 25.125 | 25.125 | 25.125
Kumbakonam Bypass | 9.9512 | 0 | 0
Reconstruction of Tsunami Bridge | 1.4072 | 0 | 0
Total | 432.1424 | 420.4722 | 420.4722
Status on transfer of Government Land :
Package | Area required (Hect.) | Area transfered as on 31.12.2009
01 | 125.3509 | 125.3509
02 | 27.5234 | 27.5234
03 | 33.8033 | 33.8033
04 | 10.3311 | 10.3311
05 | 12.27 | 12.27
Kumbakonam Bypass | 1.1219 | 1.1219
Total | 210.4006 | 210.4006

## (LA) Pac- 31.12.09
Progress for Package 01:
SI. No. | Land Requirement | Target (Hect.) | Achieved (Hect.) | Balance private land to be acquired or to be transferred from HR & CE Dept.
1 | Private land | 263.0335 | 263.0335 | 0
2 | Government Lands | 125.3509 | 125.3509 | 0
| Total | 388.3844 | 388.3844 | 0
Progress for Package 02 :
SI. No. | Land Requirement | Target (Hect.) | Achieved (Hect.) | Balance private land to be acquired under TN Highways Act or to be transferred from HR & CE Dept
1 | Private land | 87.4583 | 87.4583 | 0
2 | Government Lands | 27.5234 | 27.5234 | 0
| Total | 114.9817 | 114.9817 | 0
Progress for Package 03 :
SI. No. | Land Requirement | Target (Hect) | Achieved (Hect) | Balance private land to be acquired under TN Highways Act or to be transferred from HR & CE Dept
1 | Private land | 14.1348 | 14.1348 | 0
2 | Government Lands | 33.8033 | 33.8033 | 0
| Total | 47.9381 | 47.9381 | 0
Progress for Package 04 :
SI. No. | Land Requirement | Target (Hect) | Achieved (Hect) | Balance private land to be acquired under TN Highways Act and transferred from HR & CE
1 | Private land | 31.0324 | 31.0324 | 0
2 | Government Lands | 10.3311 | 10.3311 | 0
| Total | 41.3635 | 41.3635 | 0
Progress for Package 05 (Ramanathapuram Bypass):
SI. No. | Land Requirement | Target (Hect) | Achieved (Hect) | Balance private land under TNHW Act
1 | Private land | 25.125 | 25.125 | 0
2 | Government Lands | 12.27 | 12.27 | 0
| Total | 37.395 | 37.395 | 0
SI. No. | Land Requirement | Target (Hect) | Achieved (Hect) | Balance private land under TNHW Act
1 | Kumbakonam Bypass | 9.9512 | 0 | 9.9512
2 | Tsunami Affected bridge | 1.4072 | 0 | 1.4072
| Total | 11.3584 | 0 | 11.3584