## Upgradation Works
TAMIL NADU ROAD SECTOR PROJECT
PROCUREMENT PLAN PART B - WORKS TO BE AWARDED
I. ROAD UPGRADATION COMPONENT
| Project componet Identification code | Description of works | [10 empty] | Design/Investigation completed (Date) | Preparation of Bid document and Estimate (Date ) | Estimate Sanctioned and Bid document sent to the Bank for No Objection (Date) | Estimate Sanctioned (Value in US$/Rs.) | Bank's No Objection to Bidding Document (Date) | Bids |  | Contract award decided(Date) | Bank's No Objection to contract Award (Date) | Approval of Government for entrustment (Date) | Contract signed (Date) | Name of Contractor / Nationality | WBR No. | Contract No., Value of contract & currency | Commencement of Work (Date) | Target Date of completion (Date)
|  | Package No. | Description of Package | Length in km | Base Cost Million Rs. | Base Cost Million US$ | Physical and Price Contingency Million Rs. | Physical and Price Contingency Million US$ | Total Cost including Contingency Million Rs. | Total Cost including Contingency Million US$ | Contract Period in months | Method of Procurement ICB/NCB | [5 empty] | Invitation (Date) | Opened on (Date)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 23 | 24 | 25 | 26 | 27 | 28
A. Road Upgradation Component
PP | CA5** | TNRSP 05 | Extended portion in Kumbakonam bypass | 5 | 200 | 4.1667 | 31.125 | 0.64844 | 231.125 | 4.8151 | 12 | NCB | 2003-11-20 | 2003-12-31 | 2003-12-15 | 4.9125 | 2004-01-15 | 2004-01-30 | 2004-03-05 | 2004-03-25 | 2004-04-09 |  | 2004-05-09 |  |  |  | 2004-06-08 | 2005-11-30
2003-12-15
R1 | Method of Procurement ICB/NCB 14: 2004-10-15; Method of Procurement ICB/NCB 15: 2004-10-30; Method of Procurement ICB/NCB 16: 2004-11-07; Method of Procurement ICB/NCB 18: 2004-11-22; Invitation (Date) 19: 2004-12-02; Opened on (Date) 20: 2005-01-16; Opened on (Date) 21: 2005-03-02; Opened on (Date) 22: 2005-03-17; Opened on (Date) 23: 2005-04-06; Opened on (Date) 23: 2005-04-17; Opened on (Date) 27: 2005-05-17; Opened on (Date) 28: 2006-11-08
R2 | Method of Procurement ICB/NCB 14: 2005-05-15; Method of Procurement ICB/NCB 15: 2005-06-14; Method of Procurement ICB/NCB 16: 2005-06-21; Method of Procurement ICB/NCB 18: 2005-07-06; Invitation (Date) 19: 2005-07-13; Opened on (Date) 20: 2005-08-27; Opened on (Date) 21: 2005-10-26; Opened on (Date) 22: 2005-11-10; Opened on (Date) 23: 2005-12-10; Opened on (Date) 27: 2005-12-17; Opened on (Date) 28: 2007-06-10
R3 | Method of Procurement ICB/NCB 14: 2005-11-15; Method of Procurement ICB/NCB 15: 2005-12-15; Method of Procurement ICB/NCB 16: 2005-12-22; Method of Procurement ICB/NCB 18: 2006-01-06; Invitation (Date) 19: 2006-01-07; Opened on (Date) 20: 2006-02-21; Opened on (Date) 21: 2006-04-07; Opened on (Date) 22: 2006-04-22; Opened on (Date) 23: 2006-05-07; Opened on (Date) 27: 2006-05-14; Opened on (Date) 28: 2007-11-05
R4 | Method of Procurement ICB/NCB 14: 2006-04-15; Method of Procurement ICB/NCB 15: 2006-05-15; Method of Procurement ICB/NCB 16: 2006-05-22; Method of Procurement ICB/NCB 18: 2006-06-06; Invitation (Date) 19: 2006-06-07; Opened on (Date) 20: 2006-07-22; Opened on (Date) 21: 2006-09-05; Opened on (Date) 22: 2006-09-20; Opened on (Date) 23: 2006-10-05; Opened on (Date) 23: 2006-10-05; Opened on (Date) 27: 2006-10-12; Opened on (Date) 28: 2008-04-04
R5 | Method of Procurement ICB/NCB 14: 2006-09-30; Method of Procurement ICB/NCB 15: 2006-10-30; Method of Procurement ICB/NCB 16: 2006-11-06; Method of Procurement ICB/NCB 18: 2006-11-21; Invitation (Date) 19: 2006-11-22; Opened on (Date) 20: 2007-01-06; Opened on (Date) 21: 2007-02-20; Opened on (Date) 22: 2007-03-07; Opened on (Date) 23: 2007-03-22; Opened on (Date) 27: 2007-03-29; Opened on (Date) 28: 2008-09-19
R6 | Method of Procurement ICB/NCB 14: 2007-04-30; Method of Procurement ICB/NCB 15: 2007-05-30; Method of Procurement ICB/NCB 16: 2007-06-06; Method of Procurement ICB/NCB 17: 235.8; Method of Procurement ICB/NCB 18: 2007-06-16; Invitation (Date) 19: 2007-06-23; Opened on (Date) 20: 2007-07-28; Opened on (Date) 21: 2007-08-27; Opened on (Date) 22: 2007-09-11; Opened on (Date) 23: 2007-09-26; Opened on (Date) 27: 2007-10-03; Opened on (Date) 28: 2009-03-26
R7 | Method of Procurement ICB/NCB 14: 2007-11-30; Method of Procurement ICB/NCB 15: 2007-12-15; Method of Procurement ICB/NCB 16: 2007-12-20; Method of Procurement ICB/NCB 18: 2007-12-30; Invitation (Date) 19: 2008-01-15; Opened on (Date) 20: 2008-02-29; Opened on (Date) 21: 2008-04-11; Opened on (Date) 22: 2008-04-26; Opened on (Date) 23: 2008-05-26; Opened on (Date) 27: 2008-06-02; Opened on (Date) 28: 2009-08-26
R8 | Method of Procurement ICB/NCB 16: 2008-05-10; Method of Procurement ICB/NCB 18: 2008-05-25; Invitation (Date) 19: 2008-05-28; Opened on (Date) 20: 2008-07-02; Opened on (Date) 21: 2008-08-01; Opened on (Date) 22: 2008-08-16; Opened on (Date) 23: 2008-08-31; Opened on (Date) 27: 2008-09-07; Opened on (Date) 28: 2009-09-02
R9 | Method of Procurement ICB/NCB 16: 2008-08-31; Method of Procurement ICB/NCB 18: 2008-09-30; Invitation (Date) 19: 2008-10-07; Opened on (Date) 20: 2008-11-21; Opened on (Date) 21: 2008-12-21; Opened on (Date) 22: 2009-01-20; Opened on (Date) 23: 2009-02-19; Opened on (Date) 27: 2009-02-26; Opened on (Date) 28: 2010-02-21
R10 | Method of Procurement ICB/NCB 16: 2009-04-15; Method of Procurement ICB/NCB 18: 2009-05-25; Invitation (Date) 19: 2009-06-08; Opened on (Date) 20: 2009-07-23; Opened on (Date) 21: 2009-09-06; Opened on (Date) 22: 2009-10-06; Opened on (Date) 23: 2009-11-05; Opened on (Date) 27: 2009-11-12; Opened on (Date) 28: 2010-11-07
A | Method of Procurement ICB/NCB 14: Detailed design, DPR, Bid docment prepared and being reviewed by PIU & World Bank.
PP | 2: CA6**; Package No. 3: PPP Support (2 to 4 contracts); Description of Package 4: Roads identified; Base Cost Million Rs. 6: 360; Base Cost Million US$ 7: 7.5; Total Cost including Contingency Million Rs. 10: 360; Total Cost including Contingency Million US$ 11: 7.5; Method of Procurement ICB/NCB 13: ICB; Method of Procurement ICB/NCB 14: Candidate roads finalised. The consultant has completed the techno-economic feasibility for 5 roads. Based on the feasibility, procurement of Chennai ORR sub project under BOT/ Annuity model is in progress. Thus procurement of sub projects does not arise.
R
A
* PP: Target dates agreed as per Procurement Plan | Physical and Price Contingency Million Rs. 8: R.Revision 1,2 etc; Method of Procurement ICB/NCB 13: A:Actual dates; Method of Procurement ICB/NCB 17: WBR No: World Bank Reference Number
** Applicable license of 'Prior Review' by Bank
28.8

## Upgradation Services
TAMIL NADU ROAD SECTOR PROJECT
PROCUREMENT PLAN - PART B - CONSULTANCY SERVICES TO BE AWARDED
I. ROAD UPGRADATION COMPONENT
| Project componet Identification code | Description of Services | [11 empty] | Advertising for shortlisting (Date) | TOR/shortlist to be finalised (Date) | RFP Final Draft to be forwarded to the Bank (Date) | No Objection from Bank for(a). TOR/shortlist/ (b).Final RFP (Date) | Proposals |  | Evaluation to be finalised (a) Technical (b) combined (c) Draft contract (d) Final contract (Date) | Bank's No Objection to (a) Technical (b) combined (c) Draft contract (d) Final contract Award (Date) | Approval of Government for entrustment (Date) | Contract signed (Date) | Commencement of Work (Date) |  | Services to be completed (Date) | Contract Numbers, Value and Currency | Name of Consultant/Nationality & Zip Code, if USA | WBR No.
|  | Package No. | Description of Services | Length in km | Base Cost Million Rs. | Base Cost Million US$ | Physical and Price Contingency Million Rs. | Physical and Price Contingency Million US$ | Total Cost including Contingency Million Rs. | Total Cost including Contingency Million US$ | Consultancy Period in months | Method of Selection | Estimate santioned (US$/Rs in M) |  |  |  |  | RFP issued (Date) | Receipt (Date)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 26 | 27 | 28 | 29
A. Road Upgradation Component
PP | CA 13** | SC4 | Supervision Consultancy (SC4) - Kumbakonam bypass & Reconstruction of Tsunami affected bridge |  | 15.7 | 0.32708 | 2.355 | 0.049063 | 18.055 | 0.37615 | 18 | QCBS |  |  | 2009-04-15 | 2009-04-30 | (a) 30-Apr-09 (b) 25-May-09 | 2009-06-06 | 2009-07-21 | (a) 21-Aug-09 (b) 21-Sep-09 (c) 7-Oct-09 (d) 31-Oct-09 | (a) 31-Aug-09 (b) 30-Sep-09 (c) 21-Oct-09 (d) 15-Nov-09 | Not Applicable | 2009-10-31 | 2009-11-15 |  | 2011-05-09
A | [13 empty] | 2008-10-13
Formulas:
Receipt (Date) = [RFP issued (Date)]+45

## Maintenance Works
TAMIL NADU ROAD SECTOR PROJECT
PROCUREMENT PLAN PART B - WORKS TO BE AWARDED
II. ROAD MAINTENANCE AND SAFETY WORKS COMPONENT
| Project componet Identification code | Description of works/Goods | [10 empty] | Design/Investigation completed (Date) | Preparation of Estimate and Bid document Estimate (Date) | Estimate Sanctioned (Date) | Estimate Sanctioned (Value in US$/Rs.) | Bank's No Objection to Bidding Document (Date) | Bids |  | Contract Award decided (Date) | Bank's No Objection to contract Award (Date) | Contract signed (Date) | Name of Contractor / Nationality | WBR No. | Contract Numbers, Value and Currency | Commencement of Work (Date) | Target date of completion(Date)
|  | Package No. | Description of Packages | Length in km | Base Cost Million Rs. | Base Cost Million US$ | Physical and Price Contingency Million Rs. | Physical and Price Contingency Million US$. | Total Cost including ContingencyMillion Rs. | Total Cost including Contingency Million US$ | Contract Period in months | Method of Procurement ICB/NCB | [5 empty] | Invitation (Date) | Opened On (Date)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
THIRD AND FOURTH YEAR MAINTENANCE WORKS
PP | CB03-01 | MC32 | Villupuram - Thiruvannamalai road Km 40/0 - 54/4 | 14.4 | 74.31 | 1.7693 | 11.5645 | 0.27535 | 85.8745 | 2.0446 | 12 | NCB | 2005-01-15 | 2005-01-31 | 2005-01-31 |  | 2005-02-28 | 2005-03-15 | 2005-04-19 | 2005-05-04 | 2005-05-14 | 2005-05-29 |  |  |  | 2005-06-05
R1 | [12 empty] | 2005-07-15 | 2005-08-16 | 2005-08-31 |  | 2005-09-15 | 2005-09-30 | 2005-11-04 | 2005-12-09 | 2005-12-24 | 2006-01-23 |  |  |  | 2006-01-30
R2 | [12 empty] | 2005-12-15 | 2006-01-16 | 2006-01-31 |  | 2006-02-15 | 2006-03-02 | 2006-04-06 | 2006-05-11 | 2006-05-26 | 2006-06-25 |  |  |  | 2006-07-02
R3 | [12 empty] | 2006-06-01 | 2006-07-03 | 2006-07-18 |  | 2006-08-02 | 2006-08-17 | 2006-09-21 | 2006-10-26 | 2006-11-10 | 2006-12-10 |  |  |  | 2006-12-17 | 2007-12-17
R4 | [12 empty] | 2006-12-31 | 2007-02-01 | 2007-02-16 |  | 2007-03-03 | 2007-03-18 | 2007-04-22 | 2007-05-27 | 2007-06-11 | 2007-07-11 |  |  |  | 2007-07-18 | 2008-07-17
R5 | [12 empty] | 2007-06-15 | 2007-07-17 | 2007-08-01 | 110.5 | 2007-08-16 | 2007-08-31 | 2007-10-05 | 2007-11-09 | 2007-11-24 | 2007-12-24 |  |  |  | 2007-12-31 | 2008-12-30
R6 | [12 empty] | 2007-11-15 | 2007-12-15 | 2007-12-22 |  | 2007-12-30 | 2008-01-02 | 2008-02-06 | 2008-03-22 | 2008-04-06 | 2008-05-06 |  |  |  | 2008-05-13 | 2009-05-13
R7 | [12 empty] | 2008-03-31 | 2008-04-30 | 2008-05-07 |  | 2008-05-15 | 2008-05-18 | 2008-06-22 | 2008-08-06 | 2008-08-21 | 2008-09-20 |  |  |  | 2008-09-27 | 2009-09-27
R8 | [18 empty] | 2008-08-27 | 2008-10-11 | 2008-11-10 | 2008-12-10 |  |  |  | 2008-12-17 | 2009-12-17
A | [12 empty] | 2008-05-15 | 2008-06-20 | 2008-07-11 |  | Post review | 2008-07-17 | 2008-09-10 | 2008-11-24 | Post review | Proposed for Rebid, WB NOC awaited.
PP | CB03-01 | MC32 Rebid | Villupuram - Thiruvannamalai road Km 40/0 - 54/4 | 14.4 | 74.31 | 1.7693 | 11.5645 | 0.27535 | 85.8745 | 2.0446 | 12 | NCB | 2008-05-15 | 2009-04-30 | 2009-05-15 |  | Post review | 2009-06-09 | 2009-07-14 | 2009-07-29 | 2009-08-08 | 2009-08-23 |  |  |  | 2009-08-30 | 2010-08-26
A
PP | CB03-07 | MC38 | Gobi - Savandapur road Km 0/0 - 12/6 | 12.6 | 95.83 | 2.2817 | 14.9135 | 0.35508 | 110.7435 | 2.6368 | 12 | NCB | 2005-01-15 | 2005-01-31 | 2005-01-31 |  | 2005-02-28 | 2005-03-15 | 2005-04-19 | 2005-05-04 | 2005-05-14 | 2005-05-29 |  |  |  | 2005-06-05
R1 | [12 empty] | 2005-07-15 | 2005-08-16 | 2005-08-31 |  | 2005-09-15 | 2005-09-30 | 2005-11-04 | 2005-12-09 | 2005-12-24 | 2006-01-23 |  |  |  | 2006-01-30
R2 | [12 empty] | 2005-12-15 | 2006-01-16 | 2006-01-31 |  | 2006-02-15 | 2006-03-02 | 2006-04-06 | 2006-05-11 | 2006-05-26 | 2006-06-25 |  |  |  | 2006-07-02
R3 | [12 empty] | 2006-06-01 | 2006-07-03 | 2006-07-18 |  | 2006-08-02 | 2006-08-17 | 2006-09-21 | 2006-10-26 | 2006-11-10 | 2006-12-10 |  |  |  | 2006-12-17 | 2007-12-17
R4 | [12 empty] | 2006-12-31 | 2007-02-01 | 2007-02-16 |  | 2007-03-03 | 2007-03-18 | 2007-04-22 | 2007-05-27 | 2007-06-11 | 2007-07-11 |  |  |  | 2007-07-18 | 2008-07-17
R5 | [12 empty] | 2007-06-15 | 2007-07-17 | 2007-08-01 | 101.8 | 2007-08-16 | 2007-08-31 | 2007-10-05 | 2007-11-09 | 2007-11-24 | 2007-12-24 |  |  |  | 2007-12-31 | 2008-12-30
R6 | [12 empty] | 2007-11-15 | 2007-12-15 | 2007-12-22 |  | 2007-12-30 | 2008-01-02 | 2008-02-06 | 2008-03-22 | 2008-04-06 | 2008-05-06 |  |  |  | 2008-05-13 | 2009-05-13
R7 | [12 empty] | 2008-03-31 | 2008-04-30 | 2008-05-07 |  | 2008-05-15 | 2008-05-18 | 2008-06-22 | 2008-08-06 | 2008-08-21 | 2008-09-20 |  |  |  | 2008-09-27 | 2009-09-27
R8 | [18 empty] | 2008-08-27 | 2008-10-11 | 2008-11-10 | 2008-12-10 |  |  |  | 2008-12-17 | 2009-12-17
A | [12 empty] | 2008-05-15 | 2008-06-20 | 2008-06-30 |  | Post review | 2008-07-17 | 2008-09-10 | 2008-11-24 | Post review | Proposed for Rebid, WB NOC obtained on …. Rebid invited.
PP | CB03-07 | MC38 Rebid | Gobi - Savandapur road Km 0/0 - 12/6 | 12.6 | 95.83 | 2.2817 | 14.9135 | 0.35508 | 110.7435 | 2.6368 | 12 | NCB | [6 empty] | 2009-06-07 | 2009-07-07 |  | 2009-08-21 |  |  |  | 2009-08-28 | 2010-08-27
A | [12 empty] | 2008-05-15 | 2008-06-20 | 2008-06-30 | 99.8 | Post review | 2009-02-15 |  |  | Post review
PP | CB03-09 | MC40 | Arcot - Tindivanam road Km 0/0 - 21/6 | 21.6 | 101.39 | 2.414 | 15.7788 | 0.37569 | 117.1688 | 2.7897 | 12 | NCB | 2005-01-15 | 2005-01-31 | 2005-01-31 |  | 2005-02-28 | 2005-03-15 | 2005-04-19 | 2005-05-04 | 2005-05-14 | 2005-05-29 |  |  |  | 2005-06-05
R1 | [12 empty] | 2005-07-15 | 2005-08-16 | 2005-08-31 |  | 2005-09-15 | 2005-09-30 | 2005-11-04 | 2005-12-09 | 2005-12-24 | 2006-01-23 |  |  |  | 2006-01-30
R2 | [12 empty] | 2005-12-15 | 2006-01-16 | 2006-01-31 |  | 2006-02-15 | 2006-03-02 | 2006-04-06 | 2006-05-11 | 2006-05-26 | 2006-06-25 |  |  |  | 2006-07-02
R3 | [12 empty] | 2006-06-01 | 2006-07-03 | 2006-07-18 |  | 2006-08-02 | 2006-08-17 | 2006-09-21 | 2006-10-26 | 2006-11-10 | 2006-12-10 |  |  |  | 2006-12-17 | 2007-12-17
R4 | [12 empty] | 2006-12-31 | 2007-02-01 | 2007-02-16 |  | 2007-03-03 | 2007-03-18 | 2007-04-22 | 2007-05-27 | 2007-06-11 | 2007-07-11 |  |  |  | 2007-07-18 | 2008-07-17
R5 | [12 empty] | 2007-06-15 | 2007-07-17 | 2007-08-01 | 107.5 | 2007-08-16 | 2007-08-31 | 2007-10-05 | 2007-11-09 | 2007-11-24 | 2007-12-24 |  |  |  | 2007-12-31 | 2008-12-30
R6 | [12 empty] | 2007-11-15 | 2007-12-15 | 2007-12-22 |  | 2007-12-30 | 2008-01-02 | 2008-02-06 | 2008-03-22 | 2008-04-06 | 2008-05-06 |  |  |  | 2008-05-13 | 2009-05-13
R7 | [12 empty] | 2008-03-31 | 2008-04-30 | 2008-05-07 |  | 2008-05-15 | 2008-05-18 | 2008-06-22 | 2008-08-06 | 2008-08-21 | 2008-09-20 |  |  |  | 2008-09-27 | 2009-09-27
R8 | [18 empty] | 2008-08-27 | 2008-10-11 | 2008-11-10 | 2008-12-10 |  |  |  | 2008-12-17 | 2009-12-17
A | [12 empty] | 2008-05-15 | 2008-06-20 | 2008-06-30 |  | Post review | 2008-07-17 | 2008-09-10 | 2008-11-24 | Post review | Proposed for Rebid, WB NOC awaited.
PP | CB03-09 | MC40 Rebid | Arcot - Tindivanam road Km 0/0 - 21/6 | 21.6 | 101.39 | 2.414 | 15.7788 | 0.37569 | 117.1688 | 2.7897 | 12 | NCB | 2008-05-15 | 2009-04-30 | 2009-05-15 |  | Post review | 2009-06-09 | 2009-07-14 | 2009-07-29 | 2009-08-08 | 2009-08-23 |  |  |  | 2009-08-30 | 2010-08-26
A
PP | CB03-12 | MC43 | Kallakurichi - Thiruvannamalai road Km 30/0 - 41/3 | 11.3 | 77.83 | 1.8531 | 12.1123 | 0.28839 | 89.9423 | 2.1415 | 12 | NCB | 2005-01-15 | 2005-01-31 | 2005-01-31 |  | 2005-02-28 | 2005-03-15 | 2005-04-19 | 2005-05-04 | 2005-05-14 | 2005-05-29 |  |  |  | 2005-06-05
R1 | [12 empty] | 2005-07-15 | 2005-08-16 | 2005-08-31 |  | 2005-09-15 | 2005-09-30 | 2005-11-04 | 2005-12-09 | 2005-12-24 | 2006-01-23 |  |  |  | 2006-01-30
R2 | [12 empty] | 2005-12-15 | 2006-01-16 | 2006-01-31 |  | 2006-02-15 | 2006-03-02 | 2006-04-06 | 2006-05-11 | 2006-05-26 | 2006-06-25 |  |  |  | 2006-07-02
R3 | [12 empty] | 2006-06-01 | 2006-07-03 | 2006-07-18 |  | 2006-08-02 | 2006-08-17 | 2006-09-21 | 2006-10-26 | 2006-11-10 | 2006-12-10 |  |  |  | 2006-12-17 | 2007-12-17
R4 | [12 empty] | 2006-12-31 | 2007-02-01 | 2007-02-16 |  | 2007-03-03 | 2007-03-18 | 2007-04-22 | 2007-05-27 | 2007-06-11 | 2007-07-11 |  |  |  | 2007-07-18 | 2008-07-17
R5 | [12 empty] | 2007-06-15 | 2007-07-17 | 2007-08-01 | 83 | 2007-08-16 | 2007-08-31 | 2007-10-05 | 2007-11-09 | 2007-11-24 | 2007-12-24 |  |  |  | 2007-12-31 | 2008-12-30
R6 | [12 empty] | 2007-11-15 | 2007-12-15 | 2007-12-22 |  | 2007-12-30 | 2008-01-02 | 2008-02-06 | 2008-03-22 | 2008-04-06 | 2008-05-06 |  |  |  | 2008-05-13 | 2009-05-13
R7 | [12 empty] | 2008-03-31 | 2008-04-30 | 2008-05-07 |  | 2008-05-15 | 2008-05-18 | 2008-06-22 | 2008-08-06 | 2008-08-21 | 2008-09-20 |  |  |  | 2008-09-27 | 2009-09-27
R8 | [18 empty] | 2008-08-27 | 2008-10-11 | 2008-11-10 | 2008-12-10 |  |  |  | 2008-12-17 | 2009-12-17
A | [12 empty] | 2008-05-15 | 2008-06-20 | 2008-06-30 |  | Post review | 2008-07-17 | 2008-09-10 | 2008-11-24 | Post review | Proposed for Rebid, WB NOC awaited.
PP | CB03-12 | MC43 | Kallakurichi - Thiruvannamalai road Km 30/0 - 41/3 | 11.3 | 77.83 | 1.8531 | 12.1123 | 0.28839 | 89.9423 | 2.1415 | 12 | NCB | 2008-05-15 | 2009-04-30 | 2009-05-15 |  | Post review | 2009-06-09 | 2009-07-14 | 2009-07-29 | 2009-08-08 | 2009-08-23 |  |  |  | 2009-08-30 | 2010-08-26
A
Performance Based Contracts
PP | CB05-01 |  | Performance based maintenance contracts | 75 | 150 | 3.125 | 23.3438 | 0.48633 | 173.3438 | 3.6113 | 60 | NCB | 2006-01-15 | 2006-01-31 | 2006-01-31 |  | 2006-02-28 | 2006-03-15 | 2006-04-19 | 2006-05-04 | 2006-05-14 | 2006-05-29 |  |  |  | 2006-06-05
R1 |  | MC44 | [10 empty] | 2006-07-15 | 2006-08-16 | 2006-08-31 |  | 2006-09-15 | 2006-09-30 | 2006-11-04 | 2006-12-09 | 2006-12-24 | 2007-01-23 |  |  |  | 2007-01-30
R2 | [12 empty] | 2006-07-01 | 2006-08-02 | 2006-08-17 |  | 2006-09-01 | 2006-09-16 | 2006-10-21 | 2006-11-25 | 2006-12-10 | 2007-01-09 |  |  |  | 2007-01-16
R3 | [12 empty] | 2006-12-31 | 2007-02-01 | 2007-02-16 |  | 2007-03-03 | 2007-03-18 | 2007-04-22 | 2007-05-27 | 2007-06-11 | 2007-07-11 |  |  |  | 2007-07-18 | 2008-07-17
R4 | [12 empty] | 2007-08-01 | 2007-09-02 | 2007-09-17 |  | 2007-10-02 | 2007-10-17 | 2007-11-21 | 2007-12-26 | 2008-01-10 | 2008-02-09 |  |  |  | 2008-02-16 | 2009-02-15
R5 | [12 empty] | 2007-11-15 | 2007-12-17 | 2007-12-24 |  | 2008-01-01 | 2008-01-08 | 2008-02-12 | 2008-03-13 | 2008-03-28 | 2008-04-27 |  |  |  | 2008-05-04 | 2009-05-04
R6 | [12 empty] | 2008-03-31 | 2008-05-15 | 2008-05-22 |  | 2008-05-30 | 2008-06-06 | 2008-07-21 | 2008-08-20 | 2008-09-04 | 2008-10-04 |  |  |  | 2008-10-11 | 2013-10-10
R7 | [12 empty] | 2008-09-30 | 2008-11-14 | 2008-11-21 |  | 2008-11-29 | 2008-12-06 | 2009-01-20 | 2009-02-19 | 2009-03-06 | 2009-04-05 |  |  |  | 2009-04-12 | 2014-04-11
R8 | [14 empty] | 2009-02-28 |  | 2009-05-25 | 2009-06-09 | 2009-07-24 | 2009-09-07 | 2009-10-07 | 2009-11-06 |  |  |  | 2009-11-13 | 2014-11-12
A
PP | CB09-3-4 | 3 to 4 contracts | Minor Improvement works and Education (Will be taken up based on the output of Road Safety Audit) | [8 empty] | DC/NS/CQS | 2005-05-05 | 2005-06-04 | 2005-06-11 |  | 2005-06-26 | 2005-07-06 | 2005-08-14 | 2005-09-09 | 2005-09-24 | 2005-10-24 |  |  |  | 2005-10-31
R1 |  |  |  |  | 100 | 2.0833 | 15.5625 | 0.32422 | 115.5625 | 2.4076 | 9 |  | 2005-06-01 | 2005-07-01 | 2005-07-21 |  | 2005-08-05 | 2005-08-27 | 2005-10-01 | 2005-11-15 | 2005-11-30 | 2005-12-30 |  |  |  | 2006-01-06
R2 | [12 empty] | 2005-10-15 | 2005-10-30 | 2005-11-06 |  | Post Review | 2005-11-15 | 2005-12-24 | 2006-01-19 | 2006-02-03 | 2006-03-05 |  |  |  | 2006-03-12
R3 | [12 empty] | 2006-07-01 | 2006-07-31 | 2006-08-07 |  | Post Review | 2006-08-14 | 2006-09-18 | 2006-11-02 | 2006-11-17 | 2006-12-17 |  |  |  | 2006-12-24 | 2007-09-23 18:00
R4 | [12 empty] | 2007-06-15 | 2007-07-15 | 2007-07-22 |  | Post Review | 2007-07-29 | 2007-09-02 | 2007-10-17 | Post Review | 2007-11-21 |  |  |  | 2007-11-28 | 2008-08-27 18:00
A
PP | CB09-3-4 | 2 | Implementataion of short Term remedial measures based on findings of RSA (about 3 contracts) |  | 54.52 | 1.1358 | 8.4847 | 0.17676 | 63.0047 | 1.3126 | 12 | NCB |  | 2009-01-15 | 2009-01-18 |  | Post Review | 2009-01-28 | 2009-02-27 | 2009-03-29 | Post Review | 2009-04-05 |  |  |  | 2009-04-12 | 2009-09-09
R1 | [12 empty] | 2009-03-31 | 2009-04-30 | 2009-05-10 |  | 2009-05-20 | 2009-06-01 | 2009-07-01 | 2009-07-31 | 2009-08-15 | 2009-08-30 |  |  |  | 2009-09-06 | 2010-02-03
R2 | [12 empty] | 2009-10-14 | 2009-10-14 | 2009-10-14 |  |  | 2009-10-29 | 2009-11-28 | 2009-12-13 |  | 2009-12-23 |  |  |  | 2009-12-30 | 2010-03-30
A
PP |  |  | Reconstruction of Tsunami affected bridge connecting Keelamanakudi and Melamanakudi villages |  | 202 | 4.8095 | 31.4362 | 0.74848 | 233.4363 | 5.558 | 18 | NCB | 2007-03-12 | 2007-05-12 | 2007-05-22 |  | Post Review. However Technical Specification to be reviewed by the Bank. | 2007-06-11 | 2007-07-16 | 2007-08-10 | Post Review | 2007-09-14 |  |  |  | 2007-09-21 | 2009-03-21 12:00
R1 | [12 empty] | 2007-04-30 | 2007-05-15 | 2007-05-20 |  | Post Review. However Technical Specification to be reviewed by the Bank. | 2007-05-30 | 2007-07-04 | 2007-08-18 | Post Review | 2007-09-22 |  |  |  | 2007-09-29 | 2009-03-29 12:00
R2 | [12 empty] | 2007-10-30 | 2007-11-30 | 2007-12-15 |  |  | 2008-01-02 | 2008-03-02 | 2008-05-01 | Post Review | 2008-05-31 |  |  |  | 2008-06-07 | 2009-12-06 12:00
R3 | [12 empty] | 2008-03-31 | 2008-04-14 | 2008-04-21 |  | 2008-05-05 | 2008-05-08 | 2008-06-12 | 2008-06-26 | 2008-07-10 | 2008-07-31 |  |  |  | 2008-08-07 | 2010-02-05 12:00
R4 | [12 empty] | 2008-10-31 | 2008-11-14 | 2008-11-21 |  | 2008-12-21 | 2008-12-24 | 2009-02-07 | 2009-03-09 | 2009-04-08 | 2009-05-08 |  |  |  | 2009-05-15 | 2010-11-13 12:00
R5 | [17 empty] | 2009-06-06 | 2009-07-21 | 2009-09-04 | 2009-10-04 | 2009-11-03 |  |  |  | 2009-11-10 | 2011-05-11 12:00
A | [16 empty] | 2008-10-02
* PP: Target dates agreed as per Procurement Plan | [6 empty] | R.Revision 1,2 etc | [5 empty] | A:Actual dates |  |  |  | WBR No: World Bank Reference Number
** Applicable license of 'Prior Review' by Bank
Formulas:
Bids = [Estimate Sanctioned (Date)]+7
Contract signed (Date) = [Contract Award decided (Date)]+45
Contract signed (Date) = [Contract Award decided (Date)]+28+7
Commencement of Work (Date) = [Contract signed (Date)]+7
Target date of completion(Date) = [Commencement of Work (Date)]+365
Target date of completion(Date) = [Commencement of Work (Date)]+365*5

## Maintenance Services
TAMIL NADU ROAD SECTOR PROJECT
PROCUREMENT PLAN PART B - SERVICES TO BE AWARDED
II. ROAD MAINTENANCE AND SAFETY WORKS COMPONENT
| Project componet Identification code | Description of Services | [11 empty] | Advertising for shortlisting (Date) | TOR/shortlist to be finalised (Date) | RFP Final Draft to be forwarded to the Bank (Date) | No Objection from Bank for(a). TOR/shortlist/ (b).Final RFP (Date) | Proposals |  | Evaluation to be finalised (a) Technical (b) combined (c) Draft contract (d) Final contract (Date) | Bank's No Objection to (a) Technical (b) combined (c) Draft contract (d) Final contract Award (Date) | Approval of Government for entrustment (Date) | Contract signed (Date) | Commencement of Work (Date) |  | Services to be completed (Date) | Contract Numbers, Value and Currency | Name of Consultant/Nationality & Zip Code, if USA | WBR No.
|  | Package No. | Description of Services | Length in km | Base Cost Million Rs. | Base Cost Million US$ | Physical and Price Contingency Million Rs. | Physical and Price Contingency Million US$ | Total Cost including Contingency Million Rs. | Total Cost including Contingency Million US$ | Estimated value Million US$/INR | Consultancy Period in months | Method of Selection |  |  |  |  | RFP issued (Date) | Receipt (Date)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
pp | 2: CB11**; 4: PBMC supervision / monitoring consultant; 6: 25; 7: 0.52083; 8: 3.8906; 9: 0.081055; 10: 28.8906; 11: 0.60189; 14: QCBS; 15: Scope of work to be finalised. Method of procurement will be as per the loan agreement for that value.
R
A
* PP: Target dates agreed as per Procurement Plan | 8: R.Revision 1,2 etc; 14: A:Actual dates; 17: WBR No: World Bank Reference Number
** Applicable license of 'Prior Review' by Bank

## IDS Services
TAMIL NADU ROAD SECTOR PROJECT
PROCUREMENT PLAN PART B - SERVICES TO BE AWARDED
III. INSTITUTIONAL STRENGTHENING AND POLICY DEVELOPMENT COMPONENT
| Project componet Identification code | [10 empty] | Advertising for shortlisting (Date) | TOR/shortlist to be finalised (Date) | RFP Final Draft to be forwarded to the Bank (Date) | No Objection from Bank for(a). TOR/shortlist/ (b).Final RFP (Date) | Proposals |  | Evaluation to be finalised (a) Technical (b) combined (c) Draft contract (d) Final contract (Date) | Bank's No Objection to (a) Technical (b) combined (c) Draft contract (d) Final contract Award (Date) | Approval of Government for entrustment (Date) | Contract signed (Date) | Commencement of Work (Date) |  | Services to be completed (Date) | Contract Numbers, Value and Currency | Name of Consultant/Nationality & Zip Code, if USA | WBR No.
|  | Description of Services | Length in km | Base Cost Million Rs. | Base Cost Million US$ | Physical and Price Contingency Million Rs. | Physical and Price Contingency Million US$ | Total Cost including Contingency Million Rs. | Total Cost including Contingency Million US$ | Consultancy Period in months | Method of Selection |  |  |  |  | RFP issued (Date) | Receipt (Date)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 25 | 24 | 25 | 25 | 27
PP | CC07** | IT development and implementation consultant (a) P&FMS |  | 15 | 0.35714 | 1.9312 | 0.045982 | 16.9312 | 0.40312 | Consultancy Period in months 11: 18; Method of Selection 12: QCBS; Method of Selection 13: 2003-06-05; Method of Selection 14: 2003-07-15; Method of Selection 15: 2003-07-15; Method of Selection 16: 2003-07-25; RFP issued (Date) 17: 2003-07-30; Receipt (Date) 18: 2003-09-13; Receipt (Date) 19: (a)7- Oct-03 (b)30-Oct-03 (c)20-Nov-03 (d)10-Dec-03; Receipt (Date) 20: 17-Oct-03 10-Nov-03 30-Nov-03 24-Dec-03
R1 | [11 empty] | 2004-10-01 | 2004-11-20 | 2004-11-20 | 2004-12-05 | 2004-12-10 | 2005-01-24 | 2005-02-13 | 2005-02-23 | 2005-04-29 | 2005-05-06 | 2005-06-05 |  | 2008-06-04
[18 empty] | 2005-03-10 | 2005-03-20
[15 empty] | 2004-12-05 |  |  | 2005-04-04 | 2005-04-14
[18 empty] | 2005-05-06 | 2005-05-16
R2 | [11 empty] | 2005-05-02 | 2005-06-06 | 2005-06-06 | 2005-06-16 | 2005-06-21 | 2005-08-05 | 2005-08-25 | 2005-09-04 | 2005-11-08 | 2005-11-15 | 2005-12-15 |  | 2008-12-14
[18 empty] | 2005-09-19 | 2005-09-29
[18 empty] | 2005-10-14 | 2005-10-24
[18 empty] | 2005-11-15 | 2005-11-25
R3 | [11 empty] | 2005-10-15 | 2005-11-19 | 2005-11-19 | 2005-11-29 | 2005-12-04 | 2006-02-02 | 2006-02-22 | 2006-03-04 | 2006-05-08 | 2006-05-15 | 2006-06-14 |  | 2009-06-13
[18 empty] | 2006-03-19 | 2006-03-29
[18 empty] | 2006-04-13 | 2006-04-23
[18 empty] | 2006-05-15 | 2006-05-25
R4 | [11 empty] | 2006-10-15 | 2006-11-19 | 2006-11-19 | 2006-11-29 | 2006-11-29 | 2007-01-13 | 2007-02-02 | 2007-02-09 | 2007-04-09 | 2007-04-16 | 2007-05-01 |  | 2009-10-29 12:00
[18 empty] | 2007-03-03 | for information
[18 empty] | 2007-03-18 | 2007-03-25
[18 empty] | 2007-04-16 | 2007-04-26
R5 | [11 empty] | 2007-03-18 | 2007-04-22 | 2007-05-02 | 2007-05-09 | 2007-05-12 | 2007-06-26 | 2007-07-16 | 2007-07-23 | 2007-09-15 | 2007-09-22 | 2007-09-29 |  | 2009-03-29 12:00
[18 empty] | 2007-08-14 | for information
[18 empty] | 2007-08-29 | 2007-09-05
[18 empty] | 2007-09-22 | 2007-10-02
R6 | [15 empty] | 2007-09-05 | 2007-10-20 | 2007-11-09 | 2007-11-16 | 2008-01-09 | 2008-01-16 | 2008-01-23 |  | 2009-07-23 12:00
[18 empty] | 2007-12-08 | for information
[18 empty] | 2007-12-23 | 2007-12-30
[18 empty] | 2008-01-16 | 2008-01-26
R7 | [11 empty] | 2007-07-16: 2008-03-31; 2007-07-23: 2008-04-07; 2007-09-15: 2008-05-26; 2007-09-22: 2008-06-05; 2007-09-29: 2008-06-12 |  | 2009-12-11 12:00
[18 empty] | 2008-04-28 | 2008-05-05
[18 empty] | 2008-05-12 | 2008-05-19
[18 empty] | 2008-05-26 | 2008-06-02
R8 | [11 empty] | 2007-09-15: 2008-09-30; 2007-09-22: 2008-09-30; 2007-09-29: 2008-10-30 |  | 2010-04-30 12:00 | Rejected
[18 empty] | 2008-08-01 | 2008-08-16
[18 empty] | 2008-08-31 | 2008-09-15
2008-09-30
A | [12 empty] | 2007-08-09 | 2007-08-09 | 2007-08-16 | 2007-09-20 | 2007-12-17 | 2008-03-14 | 2008-05-27
PP | CC07** Rebid | P&FMS Rebid | [7 empty] | 12 | QCBS | 2008-11-23 |  |  | (a)15-Apr-09 (b)15-May-09 | 2009-06-04 | 2009-07-19 | 2009-08-13 | 2009-08-28 | 2009-11-17 | 2009-11-03 | 2009-12-03 |  | 2010-12-03
[18 empty] | 2009-09-12 | 2009-09-27
[18 empty] | 2009-10-12 | 2009-10-27
[18 empty] | 2009-11-03 | 2009-11-10
A | [11 empty] | 2007-03-18: 2008-11-23; 2007-04-22: 2009-02-04; 2007-05-02: 2009-02-04
PP | CC07** | b) GIS |  | 30 | 0.71429 | 3.8625 | 0.091964 | 33.8625 | 0.80625 | 18 | QCBS | 2007-03-18 | 2007-04-22 | 2007-05-02 | 2007-05-09 | 2007-05-12 | 2007-06-26 | 2007-07-16 | 2007-07-23 | 2007-09-15 | 2007-09-22 | 2007-09-29 |  | 2009-03-29 12:00
[18 empty] | 2007-08-14 | for information
[18 empty] | 2007-08-29 | 2007-09-05
[18 empty] | 2007-09-22 | 2007-10-02
R1 | [11 empty] | 2007-06-26: 2007-10-03; 2007-07-16: 2007-10-18; 2007-07-23: 2007-10-25; 2007-09-15: 2007-12-18; 2007-09-22: 2007-12-25; 2007-09-29: 2008-01-01 |  | 2009-07-01 12:00
[18 empty] | 2007-11-16 | for information
[18 empty] | 2007-12-01 | 2007-12-08
[18 empty] | 2007-12-25 | 2008-01-04
R2 | [11 empty] | 2007-07-16: 2008-03-15; 2007-07-23: 2008-03-22; 2007-09-15: 2008-05-10; 2007-09-22: 2008-05-20; 2007-09-29: 2008-05-27 |  | 2009-11-25 12:00
[18 empty] | 2008-04-12 | 2008-04-19
[18 empty] | 2008-04-26 | 2008-05-03
[18 empty] | 2008-05-10 | 2008-05-17
R3 | [11 empty] | 2007-09-15: 2008-08-20; 2007-09-22: 2008-08-20; 2007-09-29: 2008-09-19 |  | 2010-03-20 12:00
2008-08-13
2008-08-20
R4 | [11 empty] | 2007-09-15: Not applicable; 2007-09-22: 2009-06-13; 2007-09-29: 2009-07-13 |  | 2011-01-11 12:00
2009-05-15
[18 empty] | 2009-05-22 | 2009-06-06
A | [12 empty] | 2007-07-31 | 2007-07-31 | 2007-08-07 | 2007-08-13 | 2007-11-30 | 2008-03-06 | 2008-03-26
[18 empty] | 2008-06-25 | 2008-05-12
2008-07-17
pp | CC09 | Road Safety Specialised advisory TA a. Preparation b.Implementation - Road Safety Audit (RSA) consultancy |  | 5 | 0.10417 | 0.64375 | 0.013411 | 5.6437 | 0.11758 |  | SS/Invdl | 2007-05-12: 2009-06-15; 2007-06-26: 2009-07-15; 2007-07-16: 2009-08-14; 2007-07-23: Post Review; 2007-09-22: 2009-08-29; 2007-09-29: 2009-09-05 |  | 2009-12-04
A
pp | CC11 | Environment Management/ Assessment (may be 2 contracts) |  | 5 | 0.10417 | 0.77812 | 0.016211 | 5.7781 | 0.12038 |  | QCBS | 2007-03-18: Services are being decided. Method of procurement will be as per the loan agreement for that value and procurement plan will be prepared accordingly.
R
A
pp | CC12** | Specialist advisory consultants for PPP/ Project management (3-4 contracts) |  | 10 | 0.20833 | 1.2875 | 0.026823 | 11.2875 | 0.23516 |  | SS/Invdl | 2007-03-18: Scope of work wil be finalised as and when required. Method of procurement will be as per the loan agreement for that value and procurement plan will be prepared accordingly.
R
A
PP | CC14 | Road User Satisfaction Survey - 3 |  | 3.5 | 0.072917 | 0.525 | 0.010938 | 4.025 | 0.083854 | 6 | FBS | 2009-07-15 | 2009-08-29 | Post Review | (a)15-Sep-09 (b)Post Review | 2009-09-30 | 2009-11-14 | (a)14-Dec-09 (b)31-Jan-10 (c) 28-Feb-10 (d)30-Mar-10 | (a)14-Jan-10 (b)15-Feb-10 (c)15-Mar-10 (d)15-Apr-10 | Not applicable | 2010-03-30 | 2010-04-14 |  | 2010-10-11
A
pp | CC15** | Pre-investment studies and surveys |  | 100 | 2.0833 | 12.875 | 0.26823 | 112.875 | 2.3516 |  | QCBS | 2007-03-18: Procurement plan will be prepared as and when need arises.
R
A
PP |  | Strategic Option Study | [7 empty] | 12 | QCBS |  |  | 2009-04-30 | (a)15-Apr-09 (b)15-May-09 | 2009-07-15 | 2009-08-29 | (a)1-Oct-09 (b)21-Nov-09 (c)15-Dec-09 (d)30-Jan-10 | (a)1-Nov-09 (b)30-Nov-09 (c)15-Jan-10 (d)15-Feb-10 | Not applicable | 2010-01-30 | 2010-02-14 |  | 2011-02-13
A
* PP: Target dates agreed as per Procurement Plan |  |  |  |  | R.Revision 1,2 etc | [5 empty] | A:Actual dates | 2007-05-09: WBR No: World Bank Reference Number
** Applicable license of 'Prior Review' by Bank

## IDS Goods
TAMIL NADU ROAD SECTOR PROJECT
PROCUREMENT PLAN PART B - GOODS TO BE PROCURED
III. INSTITUTIONAL STRENGTHENING AND POLICY DEVELOPMENT COMPONENT
|  | Project componet Identification code | Description of goods | [10 empty] | Need Analysis / Road Safety Action Plan completed (Date) | Preparation of Bid document and Estimate (Date ) | Estimate Sanctioned (Date) | Estimate Sanctioned (Value in US$/Rs.) | Bank's No Objection to Bidding Document (Date) | Bids |  | Contract award decided (Date) | Bank's No objection to contract Award (Date) | Contract signed (Date) | Name of Supplier/ Nationality | WBR No. | Value of contract & Currency | commencement of Supply of goods (Date)
|  |  | Package No. | Description of goods | Quantity | Base Cost Million Rs. | Base Cost Million US$ | Physical and Price Contingency Million Rs. | Physical and Price Contingency Million US$ | Total Cost including Contingency Million Rs. | Total Cost including Contingency Million US$ | Contract Period in months | Method of Procurement ICB/NCB/S | [5 empty] | Invitation (Date) | Opened on (Date)
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
C. Institutional Strengthening and Policy Development
|  |  |  | Road Safety & other Engineering Related Equipments |  | 50 | 1.0417 | 0.23344 | 0.0048633 | 1.5 | 0
PP | PP | 2: CC01**; 4: Procurement of servers and other computer hardware for Transport Dept.; 6: 1.5; 12: 1; 14: To be procured under DGS&D shortly
A
PP | PP | 2: CC01**; 4: Procurement of GPS; 6: 48.5; 12: 2; 13: ICB/ NCB; 15: 2009-08-31; 16: 2009-08-31; 18: 2009-09-30; 19: 2009-10-07; 20: 2009-11-21; 21: 2009-12-21; 22: 2010-01-05; 23: 2010-01-12; 27: 2010-01-19
A
* PP: Target dates agreed as per Procurement Plan |  | 8: R.Revision 1,2 etc; 13: A:Actual dates; 17: WBR No: World Bank Reference Number
** Applicable license of 'Prior Review' by Bank